##### EVALUATION PLAN – DRAFT (WISP-2)

##### Evaluators

The WISP-2 external evaluation will be conducted by Dr. Carolee Matsumoto and Ms. Wende Allen.  Both Dr. Matsumoto and Ms. Allen have over 25 years of experience in STEM leadership, technical assistance, curriculum development and evaluation (see Curriculum Vitaes in Appendix).   Currently, Dr. Matsumoto is the external evaluator of the University of Massachusetts’ GK-12 Project, Watershed Integrated Science Project (WISP).  If funded, she will work with NSF and both projects and others, toward the NSF evaluation goal of “some later standardization” (RFP, p. 9).

Evaluation Process

The external WISP-2 evaluation will consist of both Formative and Summative components. Baseline data will be collected from various documents and reports including the Fellows’ applications, University records and reports, and through surveys and interviews at the beginning of each cohort group.  The Evaluators will meet regularly with the Project Design Team to: 1) define expectations for the evaluation, 2) develop shared expectations and performance indicators aligned to the Project objectives for the Fellows, GK-12 Teachers, Students, and School Districts and the various program components.  The Evaluators will also: 3) design data collection instruments and protocols, 4) collect and synthesize Formative Evaluation data for the Design Team to analyze as they continue to design and implement the program components and

5) collect, synthesize and analyze summative data for Design Team review at the end of each cohort group and at the conclusion of the Project. All evaluation instruments, procedures, and processes will be designed to meet the Guiding Principles for Evaluators from the American Evaluation Association and the Standards published by the Joint Committee on Standards for Education Evaluation.

##### Preliminary Evaluation Design

The chart below is organized to describe the preliminary evaluation design to meet the NSF GK-12 Objectives and Outcomes (RFP pages 4 and 19) and the specific goals and objectives of the proposed WISP-2.  The chart specifies preliminary performance indicators, proposed evaluation instruments and collection strategies.  The chart also describes a deliberate process for documenting data to evaluate the efficacy of the Project components; overall impacts on Fellows, GK-12 Teachers and Students, School Districts; and most importantly, changes in the faculty and the University to sustain and institutionalize the GK-12 Program design.

Evaluation of Efficacy of Project Activities

Including process for collecting and interpreting evaluative data and attributing impacts

| ### GK-12 Objectives | ### Baseline | ### Formative | #### Summative |
| --- | --- | --- | --- |
| ##### Preparation of Fellows for: STEM Science Careers AND GK-12 Knowledge/skills | Performance Indicators: BASIC DATA # of Fellows Demographics of Fellows - women - underrepresented minorities - Fellows w/disabilities Collection/Instruments: • Database from Fellows’ Applications Timeline/Responsibility: Month 3; 13; 24 by Evaluators | Performance Indicators: | Performance Indicators: BASIC DATA # Fellows completing GK-12 Program Degree of inclusiveness of GK-12 Program [women, underrepresented minorities, participants w/disabilities] Collection/Instruments: • Fellows’ Database Analysis Timeline/Responsibility: Month 12; 24 by Evaluators |

| ### GK-12 Objectives | ### Baseline | ### Formative | #### Summative |
| --- | --- | --- | --- |
|  | EFFECTS OF PROGRAM COMPONENTS FOR FELLOWS Attitudes and Expectations for: - STEM Fellowship Experience - GK-12 Experience Collecction/Instruments: • Likert-scale pre-GK-12 Assessment of Attitudes and Expectations | EFFECTS OF PROGRAM COMPONENTS FOR FELLOWS Summer Institute, Coaching, Mentoring, Topical Seminars, Monthly meetings Collection/Instruments: Likert-scale Evaluations for each project activity utilizing the NSDC (National Staff Development Council) 5 levels of professional development impact Timeline/Responsibility: On-going evaluation of each program activity by Evaluators On-going analysis/discussion/fine-tuning by Project Design Team | EFFECTS OF PROGRAM COMPONENTS FOR FELLOWS Effectiveness of Fellows’ STEM Experiences Effectiveness of Fellows’ GK-12 Training Changes in Fellows’ knowledge, skills, attitudes toward their own careers and GK-12 teaching and learning, and the GK-12 Program Collection/Instruments: • Summative Analysis of all Program Component Evaluations • Post-GK-12 Likert-scale Assessment of Attitudes and Expectations • Structured Exit Interviews of Fellows Timeline/Responsibility: Months 12, 24, 35 Evaluators Analysis of Findings by Design Team |

| ### GK-12 Objectives | ### Baseline | ### Formative | #### Summative |
| --- | --- | --- | --- |
|  | FELLOWS’ PERFORMANCE STEM Preparation: - Degree Attainment GK-12 Knowledge/skills: - Communication Skills - Teaching Skills - Team Building Skills Collection/Instruments: • Fellows’ Application: Projected Degree Date • Pre-GK-12 Knowledge/skills RUBRIC Assessment • Portfolio Design Assessment Timeline/Responsibility: Database: PIs Analysis: Evaluators | FELLOWS’ PERFORMANCE GK-12 Knowledge/skills: - Communication Skills - Teaching Skills - Team Building Skills Collection/Instruments: • Mid-year GK-12 Knowledge/skills RUBRIC Assessment • Review of Fellow’s Portfolio Entries to date Timeline/Responsibility: Months 6-9; 17-19; 31-33 Evaluators | FELLOWS’ PERFORMANCE STEM Preparation: - Degree Attainment - Fellows’ Career Placements CHANGE IN GK-12 Knowledge/skills: - Comunication Skills - Teaching Skills - Team Building Skills Collection/Instruments: • Post-GK-12 STEM Survey: - Projected Degree Date - Career Placement • Final GK-12 Knowledge/skills RUBRIC Assessment (This will also be queried in Structured Exit Interviews) Timeline/Responsibility: Months 12-15; 23-25; 35-36 Evaluators |

| ### GK-12 Objectives | ### Baseline | ### Formative | #### Summative |
| --- | --- | --- | --- |
| Improvement of K-12 STEM Instruction | Performance Indicators: TEACHERS’ ATTITUDES TOWARD STEM, SCIENTISTS /RESEARCHERS, SCIENCE TEACHING, GK-12 PROGRAM AND CHANGE IN TEACHER PRACTICES Collection/Instrument: • Pre-GK-12 Assessment RUBRIC of Teachers’ Attitudes and Current Teaching Practices • Teacher Portfolio Plan Timeline/Responsibility: Months 3; 13; 25 by Evaluators | Performance Indicators: TEACHERS’ ATTITDES TOWARD STEM, SCIENTISTS/ RESEARCHERS, SCIENCE TEACHING, GK-12 PROGRAM AND CHANGE IN TEACHER PRACTICES Collection/Instrument: • Mid-year GK-12 Assessment RUBRIC of Teachers’ Attitudes and Teaching Practices • Mid-year review of Teacher Portfolio Timeline/Responsibility: Months 9; 18; 35 by Evaluators EFFECTS OF PROGRAM COMPONENTS FOR TEACHERS Collection/Instruments: Likert-scale Evaluations for each project activity utilizing the NSDC (National Staff Development Council) 5 levels of professional development impact Timeline/Responsibility: On-going evaluations by Evaluators Analysis and fine-tuning of Components by Design Team | Performance Indicators: CHANGE IN TEACHERS’ ATTITUDES TOWARD STEM, RESEARCHERS /SCIENTISTS, STEM TEACHING, GK-12 PROGRAM AND APPLICATIONS/IMPACT OF PROGRAM COMPONENTS ON TEACHERS’ PRACTICES AS A RESULT OF GK-12 PROGRAM Collection/Instrument: • Final GK-12 Assessment RUBRIC of Teachers’ Attitudes and Teaching Practices • Summative Analysis of Evaluations of All Program Component Evaluations • Assessment of Teacher Portfolios • Structured Exit Interviews with Selected Teachers Timeline/Responsibility: Months 12; 18; 24; 35 Evaluators |

| ### GK-12 Objectives | ### Baseline | ### Formative | #### Summative |
| --- | --- | --- | --- |
|  | IMPACT ON SCHOOL DISTRICTS Collection/Instrument: • Pre-GK-12 Survey of Expectations of Principal(s); Science Directors; Superintendent/Asst. Supt. Timeline/Responsibility: Months 3; 13; 25 Evaluators GK-12 STUDENT PRIOR KNOWLEDGE OF WATERSHED SCIENCE Collection/Instrument: Pre-Assessment Survey Instrument of Content Knowledge and Research Methods Timeline/Responsibility: Months 3; 12; 25 by Evaluators |  | IMPACT ON SCHOOL DISTRICTS Collection/Instruments: • Post-GK-12 Survey of Expectations of Principals(s); Science Direcctors; Supts./Asst. Supts. Timeline/Responsibility: Months 12; 24; 35 Evaluators CHANGE IN LEVEL OF STUDENT LEARNING OF WATERSHED SCIENCE Collection/Instrument: • Post-Assessment Survey of Content Knowledge and Research Methods • Student Research Project Presentations with a RUBRIC • Structured Exit Interviews with Selected Students Timeline/Responsibility: Months 11-12; 23-24; 35-36 by Evaluators |

| ### GK-12 Objectives | ### Baseline | ### Formative | #### Summative |
| --- | --- | --- | --- |
| ###### Institutionalization of UMB GK-12 Fellowships/Program And University Commitment to Partnerships with K-12 Schools | Performance Indicators: Faculty participation University Commitment to Sustaining GK-12 Fellowships University Commitment to K-12 School Partnerships: - In STEM Departments |  | Performance Indicators: Change in amount of faculty participation and commitment to GK-12 Fellows and GK-12 Teachers/Schools/Districts Changes in University Courses, Programs, and Outreach as a result of GK-12 Program Changes in University Commitment to GK-12 Fellowships Activities and Services to GK-12 Science Teachers, schools, and districts |

| ### GK-12 Objectives | ### Baseline | ### Formative | #### Summative |
| --- | --- | --- | --- |
|  | Collection/Instruments: • Analysis of University Data to assess current STEM Faculty and University commitment to and activities with GK-12 Fellows and GK-12 Teachers/Schools/Districts • Baseline Survey to collect data to assess current commitment of STEM Departments • Survey of Teachers’ and GK-12 School District Administrators’ expectations for COSMIC Services Timeline/Responsibility: Months 1-5 Data collection: PIs/Staff Data analysis: Evaluators | Collection/Instruments: • On-going evaluations of all CUSP Science Center activities with a Likert-scale Evaluation utilizing the NSDC (National Staff Development Council) 5 levels of professional development impact | Collection/Instruments: • Analysis of University Data to assess changes in STEM Faculty and University commitment to GK-12 Fellows and GK-12 Partnerships with Teachers/Schools/Districts • Survey to collect data to assess change in level of University commitment in: - $$ devoted to GK-12 Fellowships - Support to Outreach to Schools - #s of Partnerships in place/planned • Synthesis and Analysis of all COSMIC Evaluations • Client Satisfaction Survey and Structured Interviews with COSMIC clients including school district teachers and administrators Timeline/Responsibility: Months 12-13; 24-25; 35-36 Evaluators |